## SOW chart
Strategy | Activities | Implementers |  | Costs |  | Time | Deliverables | Progress | Implementation
Priority I. | Accelerate progress for low-skilled and other workers
1.1 | Redesign developmental education. Develop alternative assessments and targeted remediation modules. | Colleges: ACC, CCA, CCD, RRCC, FRCC, PPCC, PCC, LCC, TSJC, OJC, MCC, NJC, CNCC, CMC, Aims CC. Dev Ed Faculty, State Dev Ed Coordinator | Strategy | 2650320 | start | 2012-01-01 |  | Time to completion for students in DE (based on levels of remedial need). 2,400 students will be served by new dev. Ed. Curriculum | Fifteen developmental programs redesigned.
|  |  | Equip | 0 | end | 2014-06-30 |  | Number of students who complete their required developmental sequence or alternative assessments & curriculum successfully (GPA and pass rates). Yr 1 65% student will demonstrate basic skill competency; yr 2 70%; yr 3 75% (1800). | Number of students enrolled in redesigned developmental courses. 2400 students served by DE curriculum; 4000 career services; 2000 served by career coaches
|  |  | Personnel | 1636000 | Milestone | Year 1 | Revised DE programs | Students who complete gatekeeper college-level English and math. 61% overall CCCS remedial pass rate
|  |  | Facility | 0 |  |  | Contextualized curriculum
|  |  | IT/Infra | 174800 |  |  | Accelerated curriculum
|  |  | Consultant/SME | 60000 |  |  | modularized curriculum
|  |  | Other | 46000 |  |  | Alternative assessments
[6 empty] | Years 2/3 | students complete or test out of DE
1.2 | Pilot the use of OER developmental math courses | CCD Dev Ed Faculty | Strategy | 36000 | start | 2012-01-01 |  | Number and percentage of students who complete OER developmental math courses. 61% overall CCCS remedial pass rate including in OER courses. | Faculty trained to effectively teach these courses
|  |  | Equip | 0 | end | 2012-06-01 |  | Time to completion in OER developmental math courses compared to standard developmental math courses. | One college implementing this course format
|  |  | Personnel | 36000 | Milestone | 2012-01-01 | Intro algebra pilot tested at CCD
|  |  | Facility | 0 |  | 2012-06-12 | pilot test results are evaluated
|  |  | IT /Infra | 0
|  |  | Consultant/SM | 0
Priority II. | Improve retention and achievement rates to reduce time-to-completion
2.1 | Personalized guidance. Develop statewide Energy Career Website. Develop systemic processes for identifying and referring students from workforce centers to training programs. Create internships and place students. | Colleges: ACC, CCA, CCD, RRCC, FRCC, PPCC, PCC, LCC, TSJC, OJC, MCC, NJC, CNCC, CMC, Aims CC. Career coaches. CDLE and local worforce centers, in partnership with colleges and employers | Strategy | 3268215 | start | 2012-01-01 |  | Number and percentage of students who enroll in consecutive semesters. 2106 students served in Energy | 15 career coaches hired
|  |  | Equipment | 0 | end | 2014-06-01 |  | Number of students who complete 9 credits in a program of study (concentrators). 549 total number of students who earn a degree during the period of performance | Implementation of early warnings systems (via LMS for online programs, Career Coach monitoring)
|  |  | Personnel | 1923000 | Milestone | Year 1 | CDLE develops process with workforce centers. Student receive guidance from career coach. | Number and percentage of students using these services; type of services provided. 2500 students use services provided by CLDE.
|  |  | Facility | 0 |  |  | Implementation of recised student success courses | Number of certificates and degrees completed annually. 1579 certificates or degrees earned over the life of the project.
|  |  | IT / Infra | 0 |  |  | statewide energy career website is launched | Student satisfaction with these services - more than 50% students reporting satisfied or exteremly satisfied with service
|  |  | Consultant/SME | 725000 |  | Year 2 | COETC students persist at higher rate than cohort
|  |  | Other | 0 |  | Year 3 | COETC students graduate at faster rate than cohort
Priority III. | Build programs that meet industry needs
3.1 | Build online and hybrid flexible, stackable short-term certificates and associate degree programs that lead through career pathways | RRCC, FRCC, PCC, TSJC, NJC, CMC, Aims CC. College program faculty, Employer partners, CDLE | Strategy | 5504562 | start | 2012-01-01 |  | Job placement - 300 TAA students placed in energy positions | 1500 Career Readiness Certification tests administered and completed through workforce centers
|  |  | Equipment | 0 | end | 2014-06-01 |  | Wages of students after placement - target wages $23/hour | Role of Industry in creation of energy courses
|  |  | Personnel | 3290225 | Milestone | Year 1 | Energy program content advised by employers and content experts | Number of students enrolled in Energy programs. 2106 students served in energy programs. | 1000 internship and work placement agreements created and students placed.
|  |  | Lease/Facility | 0 |  |  | Referral system in place between WF centers and colleges
|  |  | IT Infrastructure | 0 |  | Year 2 | Job and internship placements
|  |  | Consultant/SME | 1245965 |  | Year 3 | Continued placement and feedback from employers
|  |  | Other: | 0
Priority IV. | Strengthen online and technology enabled learning
4.1 | Develop hybrid and online training courses. Use OER resources where available. Develop and deploy mobile labs for hands-on training. | Colleges: RRCC, FRCC, PCC, TSJC, NJC, CMC, AIMS. Energy program faculty, instructional designers. College energy coordinators. | Strategy | 4528496 | start | 2012-01-01 |  | 2106 students enrolled in online, hybrid, and mobile lab programs | Seven online and hybrid programs developed with and without OER resources
|  |  | Equip | 3193622 | end | 2014-06-01 |  | 565 students who master technology taught in mobile labs | Three mobile lab programs
|  |  | Personnel | 473300 | Milestone | Year 1 | Energy courses designed/developed
|  |  | Facility | 0 |  |  | OER content integrated into courses
|  |  | IT/ Infra | 235800 |  |  | Mobile lab equipment ordered, labs built and ready
|  |  | Consultant/SME | 0 |  | Year 2 | Students are enrolled in energy programs
|  |  | Other | 41975 |  |  | Mobile labs are serving students statewide
[6 empty] | Year 3 | Students graduate from energy programs
Colleges' capacity for online delivery is strengthened
colleges' ccapacity to deliver hands-on training at a distance is strengthened.

## Outcome targets
| Outcome Measure | Targets for TAACCCT Program (All Participants) TARGETS WILL BE ACCEPTABLE IF THEY ARE PROVIDED: (1) FOR EACH YEAR OF THE GRANT AND FOR THE TOTAL GRANT PERIOD FOR EACH OUTCOME MEASURE BELOW (2) IN AGGREGATE FOR ALL PROGRAM PARTICIPANTS FOR EACH OUTCOME MEASURE BELOW (EVEN IF THERE ARE DISTINCT OUTCOMES FOR DIFFERENT EDUCATIONAL PROGRAMS OFFERED UNDER THE GRANT)
1 | Entered Employment Rate | Year 1: 0/0=0 | Total: 882 number of student entering employment/ 1176 the number of students completing a TAA funded program = 75% the entered employment rate within 6 months
| (Provide numerator, denominator and rate) | Year 2: 294/392 = 75%
| The number of students entering employment within the first quarter after the quarter of program completion out of the number of students who completed their programs. | Year 3: 588/784 = 75%
2 | Employment Retention Rate | Year 1: 0/0=0 | Total: 749 number of students retaining employment during the second and third quarters after program completion/ 882 the number of students who entered employment during the first quarter after the quarter of program completion = 85% emplyment retention rate
| (Provide numerator, denominator and rate) | Year 2: 249/294 = 85%
| The number of students who retained employment during the second and third quarters after program completion out of the number of students who entered employment during the first quarter after the quarter of program completion. | Year 3: 500/588 = 85%
3 | Average Earnings | Year 1: 0/0=0 | Total: $17,616,480 total six-month earnings in aggregate for all students employed in the first three quarters after the quarter of completion/ 749 the number of students who were employed in the first three quarters after the quarter of program completion = $23,520 average earnings
| (Provide numerator, denominator and average) | Year 2: $5,856,480/249= $23,520
| The average six-month earnings for the second and third quarters after program completion for students who are employed in the first, second, and third quarters after program completion. | Year 3: $11,760,000/500 = $23,520
4A* | Credit Attainment Rate - Option #1 | Year 1: 0 | Total: 31920 total number of credits earned in a one-year time period/1579 the number of students who earned credits during that one year time period = 20 rate of credit attainment
| (Provide numerator, denominator and rate) | Year 2: 10520/526=20
| The average number of credits earned in a one-year time period for students who earn any number of credits during that year. | Year 3: 21040/1052 = 20
4B* | Credit Attainment Rate - Option #2 | Year 1: n/a | Total: n/a
| (Provide numerator, denominator and rate) | Year 2: n/a
| The number of students who earn any number of credits in a one-year time period out of the number of students who were enrolled and attempted to earn credits during that same one-year time period. | Year 3: n/a
5 | Attainment of Certificates (less than one year) | Year 1: 0/0=0 | Total: 1030 total number of students who earn an industry-recognized certificate in less than on year/ 2106 the number of students who were enrolled in any certificate or degree program = 49% of students attaining a certificate in less than one year
| (Provide numerator, denominator and percentage) | Year 2: 343/702 = 49%
| The number of students who earn an industry recognized certificate in less than one year out of all students who were enrolled in any certificate or degree program. | Year 3: 686/1404 = 49%
6 | Attainment of Certificates (more than one year) | Year 1: n/a | Total: n/a - no certificates > 1 year
| (Provide numerator, denominator and percentage) | Year 2: n/a
| The number of students who earn an industry recognized certificate in more than one year out of all students who were enrolled in any certificate or degree program. | Year 3: n/a
7 | Attainment of Degrees | Year 1: 0/0=0 | Total: 549 total number of students who earn a degree during the period of performance/ 2106 the number of students who were enrolled in any certificate or degree program = 26% of students attaining a degree
| (Provide numerator, denominator and percentage) | Year 2: 183/ 702 = 26%
| The number of students who earn a degree during the grant period of performance out of all students who were enrolled in any certificate or degree program. | Year 3: 366 / 1404 = 26%